EACC 30 Oct 2025

Michael Edwards: CEC Project Manager – Edinburgh Visitor Levy Participatory Budgeting

## Summary Report: Participatory Budgeting & Visitor Levy Discussion

### Focus

To introduce and gather early feedback on the proposed use of Participatory Budgeting (PB) for allocating £1.7 million from the Edinburgh Visitor Levy over the next three years.

Key Points Discussed

#### 1. Participatory Budgeting Overview

- PB shifts decision-making power from the Council to communities.

- It is resource-intensive but valuable for community engagement and cohesion.

- The process must be tailored to local needs—not one-size-fits-all.

#### 2. Visitor Levy Context

- A 5% charge on overnight accommodation starting April 2026.

- £1.7 million allocated for PB over 3 years.

- Funds must benefit both residents and visitors.

- Aim: Spread benefits beyond the city centre, ideally by Council ward (£100,000 per ward over 3 years).

#### 3. Implementation Strategy

- Start small in Year 1 (15–20% of total budget).

- Test models in specific communities (e.g. Queensferry, Kirkliston).

- Explore collaborative models over competitive ones.

- Consider consortiums and joint projects to avoid pitting organisations against each other.

#### 4. Community Involvement

- Community Councils are key but may lack reach.

- Emphasis on inclusive engagement and clear communication.

- PB process must be meaningful, not tokenistic.

#### 5. Eligible Projects

- Must align with visitor levy legislation.

- Examples: Parks, paths, public art, community policing—if they benefit visitors.

- Context matters: e.g., a mural may qualify if part of a heritage trail.

#### 6. Next Steps

- April 2026: First year of funding begins.

- Michael Edwards to develop the PB framework with community input.

- Community Councils encouraged to gather ideas and engage local groups.

- Further meetings and consultations planned.

### Key Takeaways

- The PB process is in its early design phase—community input is essential.

- There is no fixed model; flexibility and local relevance are priorities.

- Transparency, collaboration, and tangible outcomes are critical for success.

Reference

https://local.ed.ac.uk/community-grants